## Traxidy Template
TRAXIDY Project Template |  |  |  |  | Action Task appears in the Action Issues Decisions area and the High Level Plan | Select 'Y' if mile- stone | Milestones appear on the High Level Plan and on the Project Status |  |  | Owners will be shown with their Actions in AID and listed in the Contacts |  | Ensure that any Owner Name has as associated email listed
Project Information |  |  |  | Actions/Tasks (AID) & Contacts | [8 empty] | Risks
Project Name | Project Start Date | Project End Date | Dur-ation | Parent - Work Category or Group Name | Child - Action or Task Description | Mile- stone? | Start Date | End Date | Weekdays Duration | Owner First Name | Owner Last Name | Owner Email | Risk Statement (max 500 characters) | Probability 5%-95% | Impact 1 - 5 | Impacted Key Constraint
DIY Shed Build Test for Traxidy 1 | 2024-06-15 | 2024-12-14 | 130 | Obtain the materials | Make a list of materials |  | 2024-06-15 | 2024-06-24 | 6 | Your | Name | yourname@youremailer.com | there is a risk that the materials are not all available at the store | 40 | 4 | Schedule
|  |  |  | Obtain the materials | Buy the materials |  | 2024-07-06 | 2024-07-28 | 15 |  |  |  | may need to add windows if not enough light after install | 30 | 3 | Schedule & Budget
[5 empty] | Materials obtained | Y | 2024-07-28 | 2024-07-28 | Weekend |  |  |  | risk that the blueprints show incorrect measurements | 10 | 5 | Scope & Schedule & Budget
0
|  |  |  | Foundation Construction | Level the ground with gravel |  | 2024-07-20 | 2024-08-16 | 20
|  |  |  | Foundation Construction | Build floor frame |  | 2024-08-20 | 2024-09-27 | 29 | Bobby | Builder | bbuilder@traxidy.com
[5 empty] | Foundation complete | Y | 2024-09-27 | 2024-09-27 | 1
0
|  |  |  | Building the Walls | Build walls to plan |  | 2024-09-27 | 2024-10-10 | 10 | Wallimina | Good | wallgood@traxidy.com
|  |  |  | Building the Walls | Install all walls per blueprints |  | 2024-10-10 | 2024-10-29 | 14 | Wallimina | Good | wallgood@traxidy.com
[5 empty] | Wall Installation Complete | Y | 2024-10-29 | 2024-10-29 | 1
0
|  |  |  | Putting on the Roof | Install roof trusses |  | 2024-10-29 | 2024-11-18 | 15
|  |  |  | Putting on the Roof | Install roof sheathing and shingles |  | 2024-11-18 | 2024-12-14 | 20 | Roofus | Rep | roof.rep@traxidy.com
[5 empty] | Roof Complete and Shed Complete | Y | 2024-12-14 | 2024-12-14 | Weekend
0
[9 empty] | 0 | Pat | Watcher | pat@traxidy.com
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Dur-ation = NETWORKDAYS([Project Start Date],[Project End Date])
Weekdays Duration = IF(AND(ISTEXT([Child - Action or Task Description]),[Start Date]=""),"Check Dates?",(IF(AND([Mile- stone?]="Y",[Start Date]=""),"Check Dates?",(IF(AND(NETWORKDAYS([Start Date],[End Date])=0,ISTEXT([Child - Action or Task Description])),"Weekend",(IF([End Date]<[Start Date],"Check Dates?",(IF(NETWORKDAYS([Start Date],[End Date])>32000,"Check Dates?",NETWORKDAYS([Start Date],[End Date]))))))))))
Note on E3: Traxidy: If the Parent Work Category or Group Name is left blank, the Action Task wiill upload to Traxidy without a Group or Category Name. This can be edited in Traxidy
Note on F3: Traxidy: Any number of Actions or Tasks that you want to upload into Traxidy can be added here. Include the start and end dates of the tasks. Optionally show an 'Owner' and an email of the owner, if you have one.
Note on G3: Traxidy: Indicate Y from the drop-down if the Action Task is a Milestone in the project. For a Milestone, ensure the Start Date and End date are the same.
Note on K3: Traxidy: This can be left blank if the owner of the Action Task is not known
Note on L3: Traxidy: This can be left blank if the owner of the Action Task is not known
Note on M3: Traxidy: An email is required each time an Owner is listed. An email is unique for each Owner. ONLY list the email once per owner
Note on O3: Traxidy: The Risk Statement explains the rsk in clear concise terms so that the risk can be understood and properly planned for.
Note on P3: Traxidy: Input the probability of the risk occurring from 5 to 95% in increments of 5. You can edit this later in Traxidy
Note on Q3: Traxidy Impact is from 1 (Low) to 5 (Highest) You can edit this again in Traxidy
Note on R3: Traxidy Choose the constraint(s) from the drop down list that would be most effected by the risk if it were to happen.